## Process
FY14 COMMUNITY SPECIAL BUDGET REQUESTS - STEP by STEP PROCESS
Activity |  | Dates | Role / Responsibility | Description/Comments
FY14 SO/AC/SG special Budget Kickoff - Submission window open |  | 2013-01-11
| ICANN Finance team to publish Template and Instructions on Community Wiki |  | ICANN - Finance
| Notification email to all SO/AC leaders |  | ICANN - Xavier
| Conference call schedule to review and discuss materials and process |  | ICANN - Maya
| Conference call to Community leaders to kickoff the process |  | Xavier to lead and all to participate
Submit FY14 Requests via email to controller@icann.org |  | From kickoff to April 19th 2013
| FY14 budget template properly filled and submitted to controller@icann.org |  | SO/AC/SG requestor
| The submission deadline for all budget requests is 4/19/2013 | 2013-04-19 | SO/AC/SG requestor | Incomplete application will be evaluated "As Is" by the submission deadline
| The submission deadline for the "Fast Track Request" is 3/22/2013 | 2013-03-22 | SO/AC/SG requestor | Incomplete application will be evaluated "As Is" by the submission deadline
| Monitor and review controller mailbox for So/AC/SG budget requests. Review all incoming requests and assign an application number and issue an acknowledgement receipt (email) within 2 business days and assign |  | ICANN - Finance
| Review application for completeness and post complete request on the community wiki page within 5 businees days as a application validation |  | ICANN - Finance
| Notify requestor with incomplete apllication within 5 businees with list of missing information. |  | ICANN - Finance
| Requestor to provide missing information in order to validate the application and resume the process. |  | SO/AC/SG requestor
Budget Request Evaluation
| The budget evaluation process begin once the request has been validated (complete application) and posted in the wiki workspace |  | ICANN - Finance
| Any subsequent exchange of information has to take place on the wiki space for transparency, effectiveness and efficiency purpose |  | All
| Clarification questions to be asked by ICANN evaluation team on the wiki workspace |  | ICANN - Evaluation team
| Requestor to provide answer and interact with evaluators on the wiki workspace |  | SO/AC/SG requestor
Fast Track Request with an early implementation date (by end of October 2013)
| The submission deadline for the "Fast Track Request" is 3/22/2013 | 2013-03-22 | SO/AC/SG requestor | Request "As Is" by the deadline
| Staff to complete evaluation of community requests | 2013-04-01 | ICANN - Evaluation team
| Finance to submit evaluation recommendation to Board Finance committee for approval | 2013-04-07 | ICANN - Finance
| Management/Board decision on early Requests for FY14 | 2013-04-11 | BFC
| Publication of FY14 approved request for early implementation on Wiki workspace | 2013-04-15 | ICANN - Finance
| Requestor to provide draft implementation plan for approved requests | 2013-05-01 | SO/AC/SG requestor
| ICANN staff to review and finalize implementation plan with SO/AC/SG requestor | 2013-05-10 | ICANN - Staff Liaison
| Publish approved "Fast Track Request" implementation plan on wiki workspace | 2013-05-13 | ICANN - Finance
Regular track Request submission window
| The submission deadline for all budget requests is 4/19/2013 | 2013-04-19 | SO/AC/SG requestor | Request "As Is" by the deadline
| Publish Community requests with the FY14 Draft Ops Plan and Budget | 2013-05-13 | ICANN - Finance
| Additional time for staff and community to interact and provide additional information | 5/6/13 to 5/24/13 | ICANN - Evaluation team
| Staff to complete evaluation of community requests and make recommendation to Board | 5/24/2013 to 6/18/2013 | ICANN - Evaluation team
| Publication of FY14 requests with staff evaluation and recommendation on Community Wiki workspace | 2013-06-19 | ICANN - Finance
Public Comments Period on FY14 Draft Ops Plan and Budget |  | 5/14 to 6/24/2013
Board Review and Vote on FY14 draft Ops Plan & Budget including FY14 Community Requests (approved & pending) |  | 2013-06-28 | Board
Requestor to provide draft implementation plan for approved requests |  | 2013-07-19
ICANN staff to review and finalize implementation plan with SO/AC/SG requestor |  | 2013-08-02
Publish implementation plan on wiki workspace for all approved budget requests |  | 2013-08-09
Procurement and disbursement activities related to FY14 requests |  | 5/13/13 to 7/31/14
Financial Report on FY14 Requests |  | Quarterly
Community Leaders report on Requests Deliverables/Metrics |  | Quarterly

## Timeline
FY14 Budget Timeline
Task Name | Duration | Start | Finish | Phase
Toronto Meeting | 5 days | Sun 10/14/12 | Thu 10/18/12 | Event
Revise FY14 Planning Process | 65 days | Fri 10/19/12 | Thu 1/17/13 | Phase
Revise FY14 Planning Process | 29 days | Fri 10/19/12 | Wed 11/28/12 | Draft Budget
Community review - FY14 process | 1 day | Thu 11/29/12 | Thu 11/29/12 | Community Review
Finalize FY14 SO/AC/SG Budget Request Process | 31 days | Fri 11/30/12 | Fri 1/11/13 | Special Budget Request
Community review - FY14 SO/AC/SG Budget process | 1 day | Thu 1/17/13 | Thu 1/17/13 | Community Review
FY13 in New Mgmt System | 75 days | Tue 10/23/12 | Mon 2/4/13 | Phase
FY13 Portofolio in Excel | 34 days | Tue 10/23/12 | Fri 12/7/12 | Draft Budget
FY13 Portofolio in AtTask | 27 days | Mon 12/10/12 | Tue 1/15/13 | Draft Budget
BFC Update/Review | 11 days | Mon 1/21/13 | Mon 2/4/13 | Review
Community Review - FY13 Content Overview | 11 days | Mon 1/21/13 | Mon 2/4/13 | Community Review
FY14 Budget Development | 49 days | Tue 1/1/13 | Fri 3/8/13 | Phase
FY14 Revenue Target | 11 days | Tue 1/1/13 | Tue 1/15/13 | Draft Budget
FY14 Draft Budget in Portofolio format | 23 days | Wed 1/16/13 | Fri 2/15/13 | Draft Budget
BFC Update/Review | 15 days | Mon 2/18/13 | Fri 3/8/13 | Review
Community Review - Programs/Projects | 15 days | Mon 2/18/13 | Fri 3/8/13 | Community Review
FY14 Budget Reviews | 55 days | Mon 2/18/13 | Fri 5/3/13 | Phase
Internal Budget Reviews | 20 days | Mon 2/18/13 | Fri 3/15/13 | Draft Budget
Close SO/AC/SG Fast Track Budget request Window | 1 day | Fri 3/22/13 | Fri 3/22/13 | Special Budget Request
Community Review - Draft Budget document | 25 days | Mon 3/25/13 | Fri 4/26/13 | Community Review
Beijing Meeting | 5 days | Sun 4/7/13 | Thu 4/11/13 | Event
Approval of FY14 SO/AC/SG Fast Track Budget requests | 1 day | Thu 4/11/13 | Thu 4/11/13 | Special Budget Request
Close SO/AC/SG Regular track Budget Request Window | 1 day | Fri 4/19/13 | Fri 4/19/13 | Special Budget Request
BFC Review | 5 days | Mon 4/29/13 | Fri 5/3/13 | Review
FY14 Budget Publication | 40 days | Mon 5/6/13 | Fri 6/28/13 | Phase
Finalize Budget Document | 6 days | Mon 5/6/13 | Sun 5/12/13 | Draft Budget
Publish Draft Budget | 1 day | Mon 5/13/13 | Mon 5/13/13 | Draft Budget
Community Budget Review Calls | 9 days | Tue 5/14/13 | Fri 5/24/13 | Draft Budget
Public comments | 34 days | Tue 5/14/13 | Fri 6/28/13 | Draft Budget
Board Review | 8 days | Wed 6/19/13 | Fri 6/28/13 | Draft Budget
Adopt FY14 Budget | 0 days | Fri 6/28/13 | Fri 6/28/13 | Milestone