## Slide 1: Task Force on NCUC Procedural Rules
March 27, 2017 14.00 UTC

## Slide 2: Meeting Agenda
Remaining Work
Finalizing the procedures
Public Comment Week
EC Voting

## Slide 3: Remaining Work
Sub-groups for the priority procedures should finalize before next Tuesday
I am creating a text for the remaining procedures with no assigned group

## Slide 4: Finalizing Procedures
Move the final texts to a clean page
  I will develop this document and circulate it amongst meeting attendees and those in the sub-groups

## Slide 5: Public Comment Week & EC Voting
The week of Monday April 10th to April 16th
EC will vote the week after April 17th to April 24th
Final procedures will be sent to the E-Team for publication on the new website

## Slide 6: AOB and Planning for Next Meeting
AOB
Next meeting: Tuesday April 4th at 13.00 UTC